John A. Sutter  Chapter #1841

Charter Doins Board Meeting Agenda, Meeting Date: 31MAR14

Call to Order:  s/b at or about 6:30pm

Roll Call of Board Members:

P = Present, A = Absent, X = Xcused absence

___ NGH Russell "Christ" Holder

___ VNGH Gary “Everready” Karl

___ GNR Bob Farrell

___ GDR Dean Hupp

___ Hangman Kevin "Stinky" Jenkins

___ Damn Fool Doorkeeper Paul "Sparks" Laue

___ Board Member at Large Fred "Mr Magoo" Willcox

___ Board Member at Large David "Dirty Dave" Barnett

___ Board Member at Large Kieth "Hardshell" Kinne

___ Graybeard Gary “Everready” Karl

___ Graybeard Mike “Gunshot” Young

___ Clampatriarch Bob "Iron Horse" Stevenson

Charter Doins Committee Reports - Mike "Gunshot" Young:

REPORT “1” – Facilities

Chairman: Mike "Gunshot" Young?

Committee Member(s): Walter Hales? Bob Farrell _____? _____?

- _______: need 5 canopys (for...   .)

REPORT “2” – Grounds

Chairman: Gary "Everready" Karl

Committee Member(s): Kevin Jenkins, Dean Hupp _____? _____?

- Dumpster from Ramona at Waste Management; GaryK

  - _______: Pay by: ________

- PortaPot from Mark @ Yolo Pumping Service; GaryK

  - _______: Pay by: ________

- Trash Cleanup

  - _______: ____(who?) _ check w/I.D.E.S. Portuguese Hall about borrowing 12 garbage cans **************************************GARY

  - Paul Laue will be in charge of clean up ************************PAUL

REPORT “3” – Signage - DONE

REPORT “4” – Entertainment - DONE

REPORT “5” – Libation

  - ______: $___ /keg; $___ TOTAL

  - ______: Sinage: Paul Laue will prepare and post signs in & on the trailer w/hours of operation & “NO SELF SERVE” *****************PAUL

- “Beer Trailer Overseer” - Keith Kinne *****************************KIETH

.

Charter Doins Board Meeting Agenda Continued, Meeting Date: 31MAR14

Charter Doins Committee Reports - Bob “Ironhorse” Stevenson:

REPORT “6” – Food/Cook - DONE

REPORT “7” – Plaque

  - _______: Monument design submitted to carpentry shop ***********KEVN

  - _______: Monument ready for dedication *************************KEVN

REPORT “8” – Initiation

- _____: How many people are needed for “REGULATORS” ? ****************KEVN

  - ______: Bob’s boards *******************************************BOBF

- Work projects: ******************************************************KEVN

  - ______: Weeding

  - ______: Cleaning

  - ______: depending on site...

- Work details: *******************************************************KEVN

  - ______: latrine duty

  - ______: trash/garbage

  - ______: announcements

  - ______: dinner bell

  - ______: maintenance and removal of signs

  - ______: what else?

- Golden Notes and E Clampus Vitus Now and Then hand outs for PBC's

  - ______: well? **************************************************KEVN

- ______: HOCO Black Robes – Gary Karl will provide the robes *********GARY

************************************************************************

- HOCO readers (assignments by the NGH): **********************************RUSL

REPORT “9” – Hawker

Chairman: Gary Karl

  - ______: Walter Hale? *******************************************GARY

  - ______: _____?

- Fort Sutter books:

  - ______: how many more? _____ picked up by who? ____ when? ____

REPORT “10” – Raffle

- ITEMs for the raffle:

  - ______: ... ***************************************************DAVE

- (Promotional) donations from local businesses ...

  - ______: ... ***************************************************DAVE

- What BIG TICKET ITEM(S) for the raffle?

  - ______: ... ***************************************************DAVE

Charter Doins Board Meeting Agenda Continued, Meeting Date: 31MAR14

Charter Doins Committee Reports - Russell "Christ" Holder:

REPORT “11” – Location

- Alcohol Form                             ****************************DEAN

REPORT “12” – Sign-In

- Release of Liability forms: Dean Hupp says they will have all the forms

  - Print for on-hand at sign-in table ()

    - flyer 2nd sheet (R.O.L... & Sign-In form) (send to PaulL)

    - _GARY : By  date: - jus bring’m **************************GARY

- Pre-Pay package:

  - STUFFING PARTY? ************************************************DEAN

  - ______: T-Shirt (or voucher for XXX), see attachment A.5 *******RUSL

  - ______: Sheepskin & Traveling Card *****************************BOBF

  - ______: Frame for PEANUTBUTTER’s Sheepskin *********************BOBF

  - ______: Gibson House & Heidrick Museum flyers ******************RUSL

  - ______: schedule of events *************************************RUSL

- _____: How many people are needed for Sign-in table attendants?

  - ______: Help from 1841:

    - __________: Check: ID, Person’s Non-Gratus, travl card, release of liability (complete/legible), registration form (complete/legible)

    - DeanH: review day-of forms, rcv payment, issue wrist bands

    - GeneB: A-M packets, review legibility

    - WalterHales: N-Z packets, review legibility

    - FredW: PBC registration

    - LonnieR: review legibility

    - Iggy

    - Dave Bond

    - Toro (will serve for a couple hours...)

  - __8___: Sign-in table attendants... so far...

- ______: Sign-In hours of operation:

  - Prime Time: Thurs[...],Fri[...],Sat[...],Sun[...]

  - Off  Hours: Thurs[...],Fri[...],Sat[...],Sun[...]

- ______: Number of staff at sign-in tables

  - prime time: [...]

  - off  hours: [...]

- Red-tag info: Health problems, Allergies, etc... of attendees...

  - ______: what all do we need to know? Where will we record it? How will be act on it?

- DONE__: first aid kit (in kitchen stuff); **************************GARY

- ______: print Refusal of Care Against Medical Advice, put w/1st Aid Kit; see Attachment L ***************************************************RUSL

- ______: MEDIC: Moose, Stix (911) – contact them *********************DEAN

- DONE__: Persons non-gratus list, see Attachment A.4 *****************RUSL

Charter Doins Board Meeting Agenda Continued, Meeting Date: 31MAR14

Charter Doins Committee Reports - Russell "Christ" Holder:

REPORT “13” – Charter Doins T-Shirts / Hats

Chairman: Chairman: Bob Farrell

Committee Member(s): Holder, GaryK, Dean Hupp

- REVIEW EACH OF THE FOLLOWING & estimate date of completion or “DONE”...

- 12NOV13:Dean: Gary Karl will report at [15NOV13] meeting

- _______: (next)committee meeting...

- What t-shirt ideas are there? - see attachment “K”

- Dean Hupp: We should have suggested Tee shirt designs for the December meeting and get a final approval at the Jan meeting.

- DONE__: Who is our new T-shirt artist? __ Steve Richardson ___________

- DONE__: New artist contact info: _________530-859-3967________________

- DONE__: Does new artist do printing? _____yes_________________________

- DONE__: Submit design ideas to artist:

- DONE__: get what artist has prepared tee shirt design should be completed by the first week in Feb.

- ______: T-shirts: ___ Large, ___ XL, ___ XX, ___ XXX, ___ 4X, ___ 6X

- DONE__: 20JAN14: Display the T-Shirt design prepared by Steve Richardson

- _DONE_: 21JAN14: supply RFO (“Request for Offer”) and print ready design graphic (in .jpg format) to the following printers, their cost is:

  - $__YES__ Steve Richardson

  - $_______ Screenprinters Ink

  - $_______ www.Vistaprint.com/T-Shirts

  - $_______ Creative T's and Things

  - $_______ 24 HR Shirt Printing

  - $_______ Danoc

  - $_______? printing (ask Gary Karl)

  - The contact info for the “check-on-price” list, see attachment A.2 of 140220boardmeeting

  - T-Shirt RFO ("Request for Offer") template, see attachment A.3 of 140220boardmeeting

- ______: 01MAR14: count pre-pays... tic tic tic...

- ______: 31MAR14: contract printer w/best price to do the job

- _NO___: black “Charter” T-shirts for security; for all 1841 members...?

- DONE__: pre-pay package container is what?

- HATs (cost will be $7ea, free hats for all volunteers)

  - DONE__: have been priced, considering who to go with.

  - TEXT ONLY

  - DONE__: *** 20JAN14: MANUFACTURERS CONTACTED, LEAD TIME IS: _____***

    - See, e.g., Danoc Manufacturing in Appendex A.2 of 140220boardmeeting

  - how many for volunteers ___-0-_____

  - how many for sale? _____________

  - DONE__: ddmmmyy: hat order sent to manufacturer

  - Stitch Jim Ferris of # 49 for hats

- PIN OF THE DAY (500 ea 1&1/2” pins ordered @ $2.04 ea (from China))

  - DONE__: *** 20JAN14: MANUFACTURERS CONTACTED, LEAD TIME IS: _____***

  - DONE__: ddmmmyy: pin of the day design complete

  - DONE__: ddmmmyy: pin of the day design sent to manufacturer

  - DONE__: ddmmmyy: pin of the day received from manufacturer

  - Emblematics in San Clemente for pins, w/screw on backs

Charter Doins Board Meeting Agenda Continued, Meeting Date: 31MAR14

Charter Doins Committee Reports - Russell "Christ" Holder, continued:

REPORT “14” – Security

Chairman: Chairman: Paul Laue

Committee Member(s): Kevin Jenkins, BobS, _____? _____?

- REVIEW EACH OF THE FOLLOWING & estimate date of completion or “DONE”...

- _______: (next)committee meeting...

- _NO____: __ free hats, one for each security staff volunteer

- _______: Security staff will be identifiable by what?, orange vests?

  - _______: Security staff identifying apparel ********************PAUL

- black “Charter” T-shirts for security staff

  - labeled “NOT REGULATOR”...

  - “CONTROLLER”

  - “HEAD HONCHO” / “HONCHO”

  - “DIRECTOR” / “DIRECTORATE”

  - “OVERLORD”

  - “GUARDIAN”

  - “PALADIN”

  - “VINDICATOR”

  - “SENTRY”

  - “WATCHDOG”

- DONE__: 4 handy-talkies for NGH & security team members...

  - BobS has 2

  - Dean has 2

- _NO____: golf cart for Paul?

- Security details

  - 7-10 security personnel will be needed and they will be set up on a rotating schedule

  - Trash Cleanup

    - Paul Laue is in charge of clean up ***********************PAUL

    - PBC’s (only through HOCO; through Sunday morning by Security)

  - Latrine Cleanup

    - Paul Laue will be in charge of clean up

    - PBC’s  we can ask PBC’s if they will help with the clean up on Sunday morning

  - Gate attendant and traffic control

  - Parking areas and parking attendants/assistants

  - Camping areas and camping attendants/assistants

  - Beer truck monitors, 2 people

  - Fire Guard (to guarantee community fire is out, cold)***********PAUL

- __10_: people are needed for SECURITY? ******************************PAUL

  - Help from 1841:

    - Paul Laue

    - Fred Willcox

    - Leo Miagi

    - _____?

    - Lud “Tele Tubby”

    - Aaron Bowie

    - _____?

    - _____?

    - _____?

  - ______: Help from YB1?  Contact for more help by date: ____________

- ______?

- ______?

- ______?

  - ______: Help from 49?   Contact for more help by date: ____________

- Matt? (will be at 49 hawker booth)

- Toro? (ONLY at sign-in table)

- ______?

  - ______: Help from LSD3? Contact for more help by date: ____________

- Bluecrow?

- ______?

- ______?

  - __8___: Sign-in table attendants... so far...

Charter Doins Board Meeting Agenda Continued, Meeting Date: 31MAR14

Charter Doins Committee Reports - Russell "Christ" Holder:

REPORT “15” – Publication

- _______: Policies notice... – HUH??? – WHAT’S THIS??? ***************RUSL

- _______: NOTICE: Friday – PBCs will be on setup crew ****************WHO?

REPORT “16” – Closing Ceremony/Wrap-up

- Rusl: call on GaryK

  - ______: Main bullets of presentation: **************************GARY

    - one...

    - two...

    - ...

- Rusl: call on MikeY

  - 12NOV13/Mike: presentation of the charter will come from the sublime

  - Gary how was this handled in Idaho & Oregon ? ? ****************GARY

See all you all in a couple days...

I would entertain a motion to adjourn...

KF!